## BOQ Estimate
RCC COLUMN / STRUCTURAL ALTERATION – LABOUR & MATERIAL COST ESTIMATE
Indicative budget for Nashik, Maharashtra ¦ INR ¦ Based on photo and limited information; not a structural design or contractor quotation
Sr. | Stage / Work Description | Material / Equipment Allowance (₹) | Labour / Professional Fee (₹) | Other / Disposal (₹) | Low Total (₹) | High Total (₹) | Notes / Assumptions
1 | Structural engineer site inspection, measurements, review of available drawings | 0 | 5000 | 0 |  |  | Written site assessment required
2 | Structural calculations, feasibility and written strengthening / load-transfer design | 0 | 15000 | 0 |  |  | Fee varies with complexity
3 | Temporary shoring / propping system: hire, base plates, bracing and installation materials | 12000 | 8000 | 0 |  |  | Engineer to specify; may need support through lower floors
4 | Site barricading, floor/wall protection, dust control and PPE | 4000 | 2500 | 0 |  |  | Masks, eye/ear protection, sheets, barriers
5 | Controlled concrete/steel cutting and demolition equipment allowance | 8000 | 10000 | 0 |  |  | Only if engineer approves; no DIY cutting
6 | Skilled demolition / structural crew allowance | 0 | 12000 | 0 |  |  | Crew/day allowance; actual duration site-dependent
7 | Debris loading, carrying and disposal | 0 | 3500 | 4500 |  |  | Access and quantity affect price
8 | Electrical inspection, isolation and minor wire relocation allowance | 2000 | 2500 | 0 |  |  | Electrician to verify before work
9 | Minor patching: mortar, repair compound, mesh, plaster and corner beads | 5000 | 5000 | 0 |  |  | Only for local surface reinstatement
10 | Primer, paint and finishing of affected wall/ceiling areas | 3500 | 3000 | 0 |  |  | Area-dependent
11 | Post-work engineer inspection / completion note | 0 | 5000 | 0 |  |  | Before removing temporary supports
| OPTIONAL / SITE-SPECIFIC: Structural steel transfer beam, connections, new supports/foundation and installation | TBD after design | TBD after design |  | NOT INCLUDED | NOT INCLUDED | Potentially the largest cost; engineer's design and measured quantities required.
Base estimate subtotal (excludes major transfer beam / new foundations)
Contingency allowance (15%)
Indicative base total including contingency
IMPORTANT: The above line-item allowances are preliminary placeholders. Replace with engineer/contractor quotations after a site visit.
• Safety: Photo shows ceiling/plaster distress and visible beam-like members; it cannot confirm the structural system or whether the column can be removed.
• Do not remove or cut an RCC column, beam, reinforcement, or connected member until a qualified structural engineer has inspected the site and issued a signed design/method statement.
• If a transfer beam, steel frame, new columns or foundations are required, obtain a separate engineered BOQ. These major structural works are deliberately excluded from the base total.
• Estimate assumes a small work area and ordinary access. Taxes, permissions, extensive electrical work, hidden damage, night work, and major structural replacement are excluded.
• Temporary supports must be designed and installed under engineer supervision; do not assume one floor's props are enough. Consider the load path through floors below.

## Summary
COST SUMMARY
Category | Low Estimate (₹) | High Estimate (₹)
Materials / equipment allowances
Labour / professional fees
Other / disposal
Base subtotal
Contingency 15%
Base total (major structural transfer work excluded)
Major structural steel / new supports / foundations | TBD after design | TBD after design